## Sheet1
No | Activities | Week
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Project Title Confirmation and Form 01A Submission | bar: Week 1 to Week 2
2 | Project Discussion with Supervisor | bar: Week 2 to Week 3
3 | Preliminary Research | bar: Week 2 to Week 7
4 | Research on Methodology and Technology Stack | bar: Week 5 to Week 8
5 | Progress Update with Supervisor | bar: Week 6
6 | Proposal Defense | bar: Week 7
7 | Expectation Analysis & Constraint Gathering | bar: Week 7 to Week 8
8 | System Design: Architecture, Data Model and Workflow | bar: Week 7 to Week 10
9 | FYP Interim Report Preparation | bar: Week 6 to Week 11
10 | Submission of Draft Interim Report | bar: Week 11
11 | Sprint 1: Initial Constraint Listing and Classification | bar: Week 11 to Week 12
12 | Submission of Interim Report and Progress Assessment 2 | bar: Week 12
13 | Sprint 2: Constraint Optimization Problem Modelling and Boolean Formulation | bar: Week 13 to Week 14
14 | Biweekly Review with FYP Supervisor | bar: Week 1 to Week 12
No | Activities | Week 1: Week
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Sprint 3: Development of CP-SAT Solver Function | bar: Week 1 to Week 2
2 | Sprint 4: Testing and deployment of the Seating Allocation Solver function to AWS Lambda | bar: Week 3 to Week 4
3 | Sprint 4: Dynamic Reallocation on ad hoc event module | bar: Week 3 to Week 4
4 | Sprint 5: Web Platform Integration: Admin Dashboard | bar: Week 5 to Week 6
5 | Sprint 5: Web Platform Integration: Participant Seat Lookup Interface | bar: Week 5 to Week 6
6 | Sprint 6: System Testing and Evaluation | bar: Week 7 to Week 8
7 | FYP 2 Dissertation and Technical Paper Preparation | bar: Week 7 to Week 8
8 | FYP 2 Dissertation and Technical Paper Review with FYP Supervisor | bar: Week 8 to Week 9
9 | Submission of Dissertation (Softcopy) and Technical Paper | bar: Week 10
10 | FYP VIVA Preparation | bar: Week 9 to Week 11
11 | FYP VIVA | bar: Week 12
12 | Project Dissertation Preparation (Hardcopy) | bar: Week 13
13 | Submission of Project Dissertation (Hardcopy) | bar: Week 14
14 | Biweekly Review with FYP Supervisor